## Important dates to remember: 2016 Johannesburg HOMEMAKERS Expo

| Friday, 27 November | - Full and final stand payment due. | expo@homemakers-sa.co.za Fax : 086 586 2930 |
| --- | --- | --- |
| January | - No Exhibitors Preview for 2016 – Pre show info will be communicated to all exhibitors electronically (permits/badges etc to be collected at build-up from the Organisers office. |  |
| Friday, 29 January | - Due date for Service Forms and payment for extra services. - Designer/Specialised stands – submission of plans for approval - Confirm package ordered on contract to exhibit - Expo prep & training session with your staff team | michelle@homemakers-sa.co.za Fax : 086 775 3067 |
| Friday, 29 January | - Structural Engineers Certificate - Gas Application - Certificate of Acceptability - Certificate of Compliance - Fire Retardent Letters - Occupational Health & Safety (Form 1) | michelle@homemakers-sa.co.za Fax : 086 775 3067 |
| Thursday, 11 February | - Confirm printing of brochures / pamphlets for handing out at the Expo. |  |
| Friday, 12 February | - RSVP for Exhibitor Awards Breakfast to be held 26th February. | michelle@homemakers-sa.co.za |
| Monday, 15 February | - Submit press releases to HOMEMAKERS’ press office for inclusion in Expo and media packs. - Send trade complimentary to suppliers. Send mailer to past and potential customers inviting them to visit your stand. - Arrange adequate insurance coverage for your participation at the Expo - Goods & Public Liability. - Final packing and planning of Expo build up - Final staff briefing and training session - Brief build up team/stand contractors | johandie@homemakers-sa.co.za |
| Monday, 22 February | - First Day of Build-Up. Exhibitors to register at Organiser's Office on Upper Level and receive Exhibitor Badges & Parking Permits - Build-Up Permits are handed out by Security officials at loading bays on arrival. |  |
| Tuesday, 23 February | - Second Day of Build-Up. Exhibitors to register at Organiser's Office on Upper Level and receive Exhibitor Badges & Parking Permits - Build-Up Permits are handed out by Security officials at loading bays on arrival. |  |
| Wednesday, 24 February | - Last Day of Build-Up. Stands to be completed by 22:00 in order for the venue to be cleaned by morning of 1st show day. - Build-Up Permits are handed out by Security officials at loading bays on arrival. - Ensure you have received your Exhibitor Badges & Parking Permits from the Organisers Office |  |
| Thursday, 25 February | - Expo Opens to the Public @ 10:00 - Stands to be completed by opening time to avoid further action! - Stand Judging, brief your team. - Trade Invitation valid for Thursday & Friday only. - Build-up permits no longer valid - Exhibitor Badges / Parking Permits now valid – Exhibitors to park in the Shadenet parking A/B and overflow Parking G (Northumberland Road). This will be strictly controlled on a ‘First come first serve’ basis. - EXPO CLOSES @ 19:00 |  |
| Friday, 26 February | - Expo opens to the public @ 10:00 - Trade Invitation valid for Thursday & Friday - Exhibitor Awards Breakfast – Sapphire Room, Banqueting (Access from Parking A/B/G – via Entrance 3). No access to main arena and upper level for exhibitors. - Expo Closes @ 19:00 |  |
| Saturday, 27 February | - Expo opens to the public @ 09:00 - Expo Closes @ 18:00 Plan for Sunday evening start of breakdown. | - Note show times change for Saturday and Sunday. |
| Sunday, 28 February | - Expo opens to the public @ 09:00 - Expo closes @ 18:00 - Breakdown only begins @ 18:30 until 22:00 - No exhibitors will be allowed to remove items / stands from the venue prior to close of show | - Note show times change for Saturday and Sunday. |
| Monday, 29 February | - Breakdown continues @ 08:00 to 16:00 - Breakdown permits to gain access to venue will be issued by security @ the loading bays Everything to be removed from stands by 16h00 sharp |  |